## FR
Ser | Formation | Unit | Dependent Wksp | Category | Tk BA No | Sys/ Sub Sys | Nature of Defect | Defect dt | Repair Status (Yes/ No) | Remarks
1 | D | 65 Armd Regt | W1 | A1 | 18X 0119N46 | D1 | Crack in Gun Cradle Assy | 2024-03-26 | No | Defect report has been fwd to S4 vide U100 letter No 70_401/TC/EME dt 13 Aug 2024. Joint Defect Investigation of cracked cradle has been earned out by msp team wef 03 Nov 2025 to 11 Nov 25 Closer report awaited.
2 | D | 65 Armd Regt | W1 | A1 | 18X 0119N47 | D2 | CBDM Bkn | 2023-05-11 | No | CBDM demanded on 11 May 23 By 'US. Vide Demand No- TSS/EOA/T-90/002 dt 11 May 23 and Controlled by CAFVD Kirkee Vide Cont No 4503235454 dt 06 Jan 25.
3 | D | 65 Armd Regt | W1 | A1 | 18X 0119N48 | E2 | TKN-4S fwd to F1 for upgradation | 2022-09-06 | No | Under repair at F1 wef 06 Sep 2022. Completion and collection notice not received.
4 | D | 65 Armd Regt | W1 | A1 | 18X 0119N49 | D1 | Distribution Box KR 185-35 faulty | 2025-03-20 | No | DRWO fwd to W1 vide Z1 letter No 70301/DRWO/TC/WKSP dt 31 May 2025. Unit directed vide 'U8,U100 letter No 24502/VVksp/Gen dt 07 Jan 2026 to fwd eqpl lo 'US for declaring it BER and further demand.
5 | D | 65 Armd Regt | W1 | A1 | 18X 0119N50 | E1 | TKN-4S fwd to F1 for upgradation | 2022-09-12 | No | Under repair al F1 wef 12 Sep 2022 completion and collection notice not received.
6 | D | 65 Armd Regt | W1 | A1 | 18X 0119N51 | E1 | TTM Not Working | 2025-03-27 | No | DRWO fwd to W1 vide Z1 letter No 70301/DRWO/TC/WKSP dt 31 Mav 2025.
7 | D | 65 Armd Regt | W1 | A1 | 18X 0119N52 | D1 | Control Unit K1 faulty | 2025-05-19 | No | DRWO fwd to W1 vide Z1 letter No 70301/DRWO/TC/WKSP dt 31 May 2025. Unit directed vide 'US, U100 letter No 24502/Wksp/Gen dt 07 Jan 2026 to fwd eqpt to 'US for declaring ii BER and further demand.
8 | D | 65 Armd Regt | W1 | A1 | 18X 0119N53 | T3 | TKN-4S fwd to F1 for upgradation | 2022-01-08 | No | Under repair at F1 wef 08 Jan 2022. Completion and collection notice not received.
9 | D | 65 Armd Regt | W2 | A1 | 18X 0119N54 | T3 | Amplidyne motor faulty | 2025-02-20 | No | DRWO fwd to W1 vide 'U8 DRWO No FWD/DRWO/A VEH/TECH/12/25 dt 11 Mar 25.
10 | D | 65 Armd Regt | W2 | A1 | 18X 0119N55 | D1 | Control Unit BV-185-2S | 2025-05-22 | No | Unit directed vide 'US, U100 letter No 24502/Wksp/Gen dt 07 Jan 2026 to fwd eqpt to·ua for declaring it BER and further demand.
11 | D | 65 Armd Regt | W2 | A1 | 18X 0119N56 | E1 | TKN-4S fwd to F1 for uooradallon | 2025-10-06 | No | Under repair at F1 wet 06 Oct 2022 Comoletion and collection notice not received.
12 | D | 65 Armd Regt | W2 | A1 | 18X 0119N57 | T1 | TKN-4S fwd to F1 for uooradatlon | 2025-10-06 | No | Under repair at F1 wef 06 Oct 2022 Comoletlon and collection notice not received.
13 | D | 65 Armd Regt | W2 | A1 | 18X 0119N58 | T2 | Amplidyne motor faulty | 2025-02-20 | No | DRWO fwd to W1 vide 'U8 DRWO No FWD/DRWO/A VEH/TECH/11/25 dt 11 Mar 25. Eaot denosited with W1 for r""air on 17 Mav 25.
14 | D | 65 Armd Regt | W2 | A1 | 18X 0119N59 | D1 | Control Unit K1 faulty | 2025-05-19 | No | DRWO fwd to W1 vide 21 letter No 70301/DRWO/TC/WKSP dt 31 May 2025. Unit directed vide 'U8. U100 letter No 24502/WksplGen dt 07 Jan 2026 to fwd eqpt to ·ua for declarina it BER and further demand.
15 | D | 65 Armd Regt | W2 | A1 | 18X 0119N60 | D1 | Control Unit BV 1S5-2S | 2025-03-20 | No | DRWO fwd to W1 vide 21 letter No 70301/DRWO/TC/WKSP dt 31 Mav 25.
16 | D | 65 Armd Regt | W2 | A1 | 18X 0119N61 | D1 | RF Unit N/W | 2025-09-22 | No | DRWO fwd to W2 vide 21 letter No 70301/DRWO/TC/WKSP dt 30 Oct 25..
17 | D | 65 Armd Regt | W2 | A1 | 18X 0119N62 | T3 | Control Unit K1 faulty | 19-Mav-25 | No | DRWO fwd to W1 vide 21 letter No 70301/DRWO/TC/WKSP dt 31 Mav 25.
18 | D | 65 Armd Regt | W2 | A1 | 18X 0119N63 | D2 | Control Unit BV 1S5-2S | 19-Mav-25 | No | DRWO fwd to W1 vide 21 letter No 70301/DRWO/TC/WKSP dt 31 Mav 25.
19 | D | 65 Armd Regt | W2 | A1 | 18X 0119N64 | D2 | Control Unit K1 faulty | 2025-06-03 | No | Unit directed vide 'U8, U100 letter No 24502/VVksplGen dt 07 Jan 2026 to fwd eqpt to·us for declarina it BER and further demand. Unit directed vide ·us, u1oo letter No 24502/WksplGen dt 07 Jan 2026 to fwd eqpt to ·us
20 | D | 65 Armd Regt | W2 | A1 | 18X 0135P71 | H2 | Electromagnet EMT-S1M | 2025-03-24 | No | for declarina it BER and further demand.
21 | D | 88 Armd Regt | W2 | A2 | 18X 0135P72 | H3 | PKU2-1A CBRN Sys assy | 2024-12-31 | No | DRWO fwd to W1 vide 'US DRWO No FWD/DRWO/A VEH/TECH/09/25 dt 26 Feb 25. Ennt deoosited with W1 for calibration on 29 Jul 25.
22 | D | 88 Armd Regt | W1 | A2 | 18X 0135P73 | G4 | TKN-4S fwd to F1 for uooradation | 2024-10-08 | No | Under repair at F1 wet 08 Oct 2022 Cornoletion and collection notice not received. DRWO fwd to W1 vide·us DRWO No FWD/DRWO/A VEH/TECH/09/25 dt 26 Feb 25.
23 | D | 88 Armd Regt | W1 | A2 | 18X 0135P74 | Z2 | PKU2-1A CBRN Sys assy | 2024-12-31 | No | Eaot denrn:ited with W1 for calibration on 29 Jul 25.
24 | D | 88 Armd Regt | W1 | A2 | 18X 0135P75 | H2 | TKN-4S fwd to F1 for upgradation | 2022-09-12 | No | Under repair at F1 wet 12 Sep 2022 Completion and collection notice not received.
25 | D | 88 Armd Regt | W1 | A2 | 18X 0135P76 | H3 | BPV-29 faultv | 2025-06-23 | No | DRWO fwd to W1 vide 21 letter No 70301/DRWO/TC/WKSP dt 15 Oct 25.
26 | D | 88 Armd Regt | W1 | A2 | 18X 0135P77 | Z2 | Cont unit and Mirror Unit defective | 2024-03-02 | No | DRWO fwd to W2 vide 'U8 DRWO No Fwd/A veh/114/2024 dt02 Apr 24. Eqpt Deposited to W2 for repair on 27 Dec 24.
27 | D | 88 Armd Regt | W1 | A2 | 18X 0135P78 | T2 | TKN 4s Electric unit not work | 2025-04-07 | No | DRWO fwd to W2 vide 21 letter No 70301/DRWO/TC/WKSP dt 31 Mav 25.
28 | D | 88 Armd Regt | W2 | A2 | 18X 013BH02 | T2 | RF Unit Not work | 2025-05-13 | No | DRWO fwd to W2 vide ·us DRWO No FWD/DRWO/A veh/Tech/28/25 dt 26 Feb 25. Eaot deoosited with W2 on 23 Jul 25.
29 | D | 5 (I) Armd Sqn | W2 | A2 | 18X 013BH03 | T4 | RF Unit & SA/A Mode N/w | 2025-09-16 | No | DRWO fwd to W2 vide 21 letter No 70301/DRWO/TC/WKSP dt 30 Oct 25..
30 | D | 5 (I) Armd Sqn | W2 | A2 | 18X 013BH04 | T4 | Speedometer not working | 2025-10-20 | No
31 | D | 6 Guards | W3 | A3 | 18X 013HH03 | T4 | Tl Control Unit and Mirror Unit faulty | 2025-09-03 | No | DRWO fwd to W2 vide 21 letter No 70301/DRWO/TC/WKSP dt 30 Oct 25..
32 | D | 6 Guards | W3 | A3 | 18X 013HH04 | H2 | RF Unit N/W | 2025-09-23 | No | DRWO fwd to W2 vide 21 letter No 70301/DRWO/TC/WKSP dt 30 Oct 25..
33 | D | 6 Guards | W4 | A3 | 18X 013HH05 | H3
34 | D | 65 Armd Regt | U1 | A2 | 18X 0120N64 | S2 | Tk T-72 Under BOH | 2025-06-23 | No | Tk T-72 Under BOH of U1
35 | D | 65 Armd Regt | U1 | A2 | 18X 0120N65 | S2 | Tk T-72 Under BOH | 2024-03-02 | No | Tk T-72 Under BOH of U1
36 | D | 6 Guards | CZW33 | A3 | 18X 01PMI32 | H1 | ICV BMP-II Under MR | 2025-03-24 | No | ICV BMP-II Under FR
37 | D | 6 Guards | CZW33 | A3 | 18X 01PMI33 | H2 | ICV BMP-II Under MR | 2024-12-31 | No | ICV BMP-II Under FR
38 | D | 8 Guards | W1 | A3 | 18X 013BH03 | H3 | EOA due to DRWO | 2025-06-23 | No | EOA due to DRWO fwd to W1 / W2 ABW
39 | D | 8 Guards | W1 | A3 | 18X 013BH04 | Z2 | EOA due to DRWO | 2024-03-02 | No | EOA due to DRWO fwd to W1 / W2 ABW
40 | D | 8 Guards | CZW33 | A3 | 18X 01PMI34 | T2 | Under MR | 2025-04-07 | No | Under FR

## SPARES
Ser | Formation | Unit | Dependent Wksp | Category | Tk BA No | Sys/ Sub Sys | Nature of Defect | Defect dt | Repair Status (Yes/ No) | Remarks